## CDR Modules
Module | Hours | Notes
CdrActions | 16 | Straight translation of commands to manipulate CDR actions
CdrAddGrp | 6 | Straight translation of command to add a new CDR group
CdrAddUsr | 6 | Straight translation of command to add a new CDR user
CdrBlob | 24 | CDR storage of images & other binary objects
CdrCache | 40 | Includes mutex handling & possible switch to SAX parser
CdrCheckAuth | 8 | Single CDR command
CdrCommand | 8 | Drudge work to do straight syntax translation
CdrDbConnection | 0 | No longer needed
CdrDbPreparedStatement | 0 | No longer needed
CdrDbResultSet | 0 | No longer needed
CdrDbStatement | 0 | No longer needed
CdrDelGrp | 4 | Simple translation
CdrDelUsr | 4 | Simple translation
CdrDoc | 120 | Large, complex module; analyze sections marked “temporary”
CdrDocTypes | 20 | Straight translation of commands to manipulate CDR document types
CdrDom | 16 | Analyze whether thread parser management still necessary; if not, drop
CdrExternalMap | 8 | Single CDR command
CdrFilter | 120 | Includes implementation of extensions
CdrGetDoc | 80 | Do analysis to find redundant code in other modules; check XXX sections
CdrGetGrp | 8 | Single CDR command
CdrGetTree | 8 | Single CDR command
CdrGetUsr | 8 | Single CDR command
CdrGlossaryMap | 12 | Straightfoward glossifier support
CdrLink | 120 | Large module, mostly database manipulation
CdrLinkProcs | 80 | How much use do we get from this? [Answer: Currently used 12 times.]
CdrListGrps | 4 | Simple CDR command
CdrListUsrs | 4 | Simple CDR command
CdrLog | 24 | Some thread handling involved
CdrLogoff | 4 | Simple CDR command
CdrLogon | 8 | Simple CDR command
CdrMergeProt | 32 | Build DOM tree instead of direct serialization
CdrModGrp | 8 | Single CDR command
CdrModUsr | 8 | Single CDR command
CdrParserInput | 8 | Not sure any of this will be needed; see CdrSearch modules
CdrPublish | 24 | Straight translation of command to create a new CDR publishing job
CdrRegEx | 0 | Don't think this will be needed
CdrReport | 40 | About a dozen reports, plus supporting routines
CdrSearch | 80 | One of the fuzzier pieces of the estimate; not sure how I'll parse queries
CdrSearch_tab | 0 | Part of CdrSearch; may implement the parser by hand
CdrServer | 24 | Top-level control module; handles socket communication & command dispatching
CdrSession | 16 | CDR commands for managing session objects
CdrShutdown | 4 | Trivial CDR command
CdrString | 24 | Much (but not all) provided by .NET; can't inherit from string, though
CdrSysValue | 16 | Commands to manipulate generic CDR system value table
CdrTiming | 8 | Figure out what to do with macros
CdrValidateDoc | 160 | Includes conversion of schema to standard & custom validation rule handling
CdrVersion | 120 | Do we need the label stuff? [Answer: No, it has never been used. No table rows.]
CdrXsd | 0 | Covered in CdrValidateDoc, where we'll parse the schema for custom rules
analyzeException | 8 | Small module
catchexp | 16 | Needs some research into interaction between .NET and Windows crash handling
Subtotal | 1356
Define conventions | 16 | XML usage, modularization, C# namespaces, XML namespaces, threading, etc.
Determine order | 8 | Analysis to figure out which modules to implement first
Extra for DOM building | 40 | Extra for replacing most (but perhaps not all) of the direction XML serialization
Testing/Debugging | 360
Total | 1764
Person Days | 221
Person Weeks | 44